## Sheet1
Items | Owner | Start | End | Progress | Note
Pre-Requisite Tasks
get access to aws | Husain |  |  | Pending
establish user stories | Mithun |  |  | Pending
establish the project sprint | Husain |  |  | In Progress
blocked
completed
Infrastructure on AWS
create VPC | Husain | 2021-02-16 | 2021-03-03 | Pending | depends on getting access to aws
establish a beanstalk stack | Husain | 2021-02-16 | 2021-03-03 | Pending | depends on getting access to aws
create a database instance | Husain | 2021-02-16 | 2021-03-03 | Pending | depends on getting access to aws
create security controls | Husain | 2021-02-16 | 2021-03-03 | Pending | depends on getting access to aws
load balancer | Husain | 2021-02-16 | 2021-03-03 | Pending | depends on getting access to aws
SSL certificate | Husain | 2021-02-16 | 2021-03-03 | Pending | depends on getting access to aws
remote access to instances | Husain | 2021-02-16 | 2021-03-03 | Pending | depends on getting access to aws
code pipeline | Husain | 2021-02-16 | 2021-03-03 | Pending | depends on getting access to aws
connect code pipeline with GitHub | Husain | 2021-02-16 | 2021-03-03 | Pending | depends on getting access to aws
System Design and Data processing
Application architect design |  |  |  | Pending
retrieve and process the data |  |  |  | Pending
fetch student/degree data using glue and feed our database |  |  |  | Pending
create ruby application |  |  |  | Pending
connect the application to the database |  |  |  | Pending
create rails that read and process data into JSON format |  |  |  | Pending
Cache data in Redis for display |  |  |  | Pending
Cohort Dashboard & Visualization
define user types/views | Mithun | 2021-02-22 | 2021-03-10 | Pending
Analyzing all the colleges student together by creating charts | Mithun | 2021-02-22 | 2021-03-10 | In Progress
Analyzing all the student in a college together by creating charts | Mithun | 2021-02-22 | 2021-03-10 | Pending
Analysing individual students charts and create statistics | Mithun | 2021-02-22 | 2021-03-10 | Pending